## Model 2.3 - @Risk for Excel
Model 2.3 | Used by the book Net Present Value and Risk Modelling for Projects (Hopkinson, 2016) published by Routledge
Simulation uses @Risk for Excel - visit www.palisade.com to download free trial license of the @RISK tool
A (deliberately) simple Net Present Value Risk Model
Risk Model Inputs |  |  |  |  | Apportionment | [5 empty] | Costs and benefits simulated by year
| Cost (£k) |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
| Min | Mode | Max | Simulated
Costs | 2000 | 2700 | 3500 | #NAME? | 0.5 | 0.5 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Benefits | 2000 | 3500 | 4500 | #NAME? | 0 | 0.14286 | 0.28571 | 0.28571 | 0.28571 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
NPV Results calculation | [10 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Project cost (£k) | [10 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Project benefits value (£k) | [10 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Cash flow (£k) | [10 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Discount Rate | 4%
Mid-year discount factor | [10 empty] | 0.98058 | 0.94287 | 0.9066 | 0.87173 | 0.8382
Cash flow Present Value (£k) | [10 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Cumulative NPV (£k) | [10 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Notes
1. Note that this is a deliberatedly simplified model with no decomposition of cost or benefits risk, no correlation between risks and no simulation of the effect of schedule risk.
2. Risk estimating inputs are colour coded Optimistic, Mode and Pessimistic
3. Brown font represents the Monte Carlo simulation input cells
4. Purple font represents the Monte Carlo simulation output (at Cell S20)