## Sheet1
Model 4.2 | Used by the book Net Present Value and Risk Modelling for Projects (Hopkinson, 2016) published by Gower
Space Industry Development and Production Project - Net Present Value Model (with peer review changes, including effects of inflation)
Quantified Assumptions | Modelled rate | [12 empty] | Other Project Assumptions
Project implementation (yrs) | 3 | [12 empty] | The unit's production design will not need adaptation for different customers
Sales window (yrs) | 7 | [12 empty] | Sales will be sustained at a constant rate, commencing from completion of the project implementation phase
Unit manufacturing cost (£K) | 200 | [12 empty] | Project delivery costs (other than capital assets) will be written down against profits from production sales
Unit selling price (£K) | 700
Potential unit sales per year | 20 | [12 empty] | Project-specific Risk
Sales conversion rate | 60% | [12 empty] | 1. Project delivery risk - includes risk of delay into Year 4 caused by additional design and test cycle
Chamber ops cost per day (£K) | 1.52 | [12 empty] | 2. Sales rate risk - Provision for 20% loss of overall market due to slippage of customer projects
Corporation Tax | 20% | [12 empty] | 3. Risk of slip to project delivery into Year 4 - provision for consequent loss of 50% of sales forecasts for Year 4
R&D Tax credit rate | 11% | [12 empty] | 4. Production yield risk - provision for 5% remake rate following production test
Discount rate (WACC) | 13%
Inflation | 3%
Project Impacts - Constant Cost |  |  | Apportionment | [10 empty] | Project Impacts calculated by year
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Check | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Total | Check
Project Implementation Costs |  | Total (£k)
Project management |  | 1200 | 0.33333 | 0.33333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 400 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0
Design engineering |  | 2800 | 0.5 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1400 | 840 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 0
Development units (6 Off) |  | 1200 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0
Special Tools & Test Equipment (STTE) |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0
Commissioning & Trials team |  | 3400 | 0.2 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 680 | 1700 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | 0
Chamber Operational costs (2 years) |  | 1110.36 | 0.2 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 222.072 | 555.18 | 333.108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110.36 | 0
Subtotal |  | 10710.36 | [11 empty] | 4302.072 | 4095.18 | 2313.108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10710.36 | 0
Project Impementation risk |  | 4000 | 0.083333 | 0.083333 | 0.083333 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 333.3333 | 333.3333 | 333.3333 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0
Total |  | 14710.36 | [11 empty] | 4635.4053 | 4428.5133 | 2646.4413 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14710.36 | 0
Project Implementation Cost Tax reliefs
Implementation costs tax relief |  | 2942.072 | [11 empty] | 463.5405 | 906.3919 | 707.4955 | 564.6441 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 2942.072 | 0
R&D Tax credits |  | 1618.1396 | [11 empty] | 0 | 509.8946 | 487.1365 | 291.1085 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 1618.1396 | 0
Subtotal |  | 4560.2116 | [11 empty] | 463.5405 | 1416.2865 | 1194.6319 | 855.7527 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 4560.2116 | 0
Sales | Annual rate (£) | Total (£k)
Base sales forecast | 8400 | 58800 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 0 | 58800 | 0
Sales rate risk @20% | 1680 | 11760 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 0 | 11760 | 0
Sales value net of risk |  | 47040 | [11 empty] | 0 | 0 | 0 | 6720 | 6720 | 6720 | 6720 | 6720 | 6720 | 6720 | 0 | 47040 | 0
Cost of sales | Annual rate (£) | Total (£k)
Management & Marketing | 200 | 1400 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 1400 | 0
Production cost | 2400 | 16800 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 0 | 16800 | 0
Chamber Operational costs | 30.4 | 212.8 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 30.4 | 30.4 | 30.4 | 30.4 | 30.4 | 30.4 | 30.4 | 0 | 212.8 | 0
Total |  | 18412.8 | [11 empty] | 0 | 0 | 0 | 2630.4 | 2630.4 | 2630.4 | 2630.4 | 2630.4 | 2630.4 | 2630.4 | 0 | 18412.8 | 0
Sales and operational risks |  | Total (£k)
Risk of project slip to sales - Year 4 |  | 3000 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0
Production yield risk @5% | 120 | 840 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 0 | 840 | 0
Total |  | 3840 | [11 empty] | 0 | 0 | 0 | 3120 | 120 | 120 | 120 | 120 | 120 | 120 | 0 | 3840 | 0
Tax on profit |  | Total (£k)
Operating profit on sales |  | 24787.2 | [11 empty] | 0 | 0 | 0 | 969.6 | 3969.6 | 3969.6 | 3969.6 | 3969.6 | 3969.6 | 3969.6 |  | 24787.2 | 0
Tax on profit |  | 4957.44 | [11 empty] | 0 | 0 | 0 | 193.92 | 793.92 | 793.92 | 793.92 | 793.92 | 793.92 | 793.92 |  | 4957.44 | 0
Project Impacts - With inflation |  |  | Apportionment | [10 empty] | Project Impacts calculated by year
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Check | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Total
Effect of inflation @ 3% | [13 empty] | 1.0149 | 1.0453 | 1.0767 | 1.109 | 1.1423 | 1.1765 | 1.2118 | 1.2482 | 1.2856 | 1.3242 | 1.3639
Project Implementation Costs
Project management |  |  | 0.33333 | 0.33333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 405.9557 | 418.1343 | 430.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1254.7684
Design engineering |  |  | 0.5 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1420.8448 | 878.0821 | 602.9497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2901.8766
6 Off Prototype units |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 608.9335 | 627.2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236.135
Special Tools & Test Equipment (STTE) |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1014.8892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1014.8892
Commissioning & Trials team |  |  | 0.2 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 690.1246 | 1777.0709 | 1098.2298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3565.4254
Chamber Operational costs (2 years) |  |  | 0.2 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 225.3785 | 580.3495 | 358.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164.384
Subtotal | [13 empty] | 4366.1262 | 4280.8384 | 2490.5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11137.4785
Project Implementation risk |  |  | 0.083333 | 0.083333 | 0.083333 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 338.2964 | 348.4453 | 358.8986 | 3326.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4372.6306
Total | [13 empty] | 4704.4226 | 4629.2837 | 2849.4125 | 3326.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15510.1092
Project Implementation Cost Tax reliefs
Implementation costs tax relief | [13 empty] | 470.4423 | 947.4839 | 761.7575 | 626.1885 | 342.68 | 0 | 0 | 0 | 0 | 0 | 0 | 3148.5522
R&D Tax credits | [13 empty] | 0 | 517.4865 | 509.2212 | 313.4354 | 365.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 1706.112
Subtotal | [13 empty] | 470.4423 | 1464.9704 | 1270.9787 | 939.6239 | 708.6489 | 0 | 0 | 0 | 0 | 0 | 0 | 4854.6642
Sales
Base sales forecast | 0 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 9315.573 | 9595.0402 | 9882.8914 | 10179.3781 | 10484.7595 | 10799.3022 | 11123.2813 | 0 | 71380.2257
Sales rate risk @20% | 0 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 1863.1146 | 1919.008 | 1976.5783 | 2035.8756 | 2096.9519 | 2159.8604 | 2224.6563 | 0 | 14276.0451
Sales value net of risk | [13 empty] | 0 | 0 | 0 | 7452.4584 | 7676.0321 | 7906.3131 | 8143.5025 | 8387.8076 | 8639.4418 | 8898.625 | 0 | 57104.1805
Cost of sales
Management & Marketing |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 221.7994 | 228.4533 | 235.3069 | 242.3661 | 249.6371 | 257.1262 | 264.84 | 0 | 1699.5292
Production cost |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 2661.5923 | 2741.44 | 2823.6832 | 2908.3937 | 2995.6456 | 3085.5149 | 3178.0804 | 0 | 20394.3502
Chamber Operational costs |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 33.7135 | 34.7249 | 35.7667 | 36.8397 | 37.9448 | 39.0832 | 40.2557 | 0 | 258.3284
Total | [13 empty] | 0 | 0 | 0 | 2917.1051 | 3004.6183 | 3094.7568 | 3187.5995 | 3283.2275 | 3381.7244 | 3483.1761 | 0 | 22352.2078
Sales and operational risks
Risk of project slip to sales - Year 4 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3326.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3326.9903
Production yield risk @5% |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 133.0796 | 137.072 | 141.1842 | 145.4197 | 149.7823 | 154.2757 | 158.904 | 0 | 1019.7175
Total | [13 empty] | 0 | 0 | 0 | 3460.07 | 137.072 | 141.1842 | 145.4197 | 149.7823 | 154.2757 | 158.904 | 0 | 4346.7079
Tax on profit
Operating profit on sales | [13 empty] | 0 | 0 | 0 | 1075.2833 | 4534.3418 | 4670.3721 | 4810.4833 | 4954.7978 | 5103.4417 | 5256.5449 | 0 | 30405.2649
Tax on profit | [13 empty] | 0 | 0 | 0 | 107.5283 | 560.9625 | 920.4714 | 948.0855 | 976.5281 | 1005.8239 | 1035.9987 | 525.6545 | 6081.053
NPV Results calculation | [13 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 |  | Total | Check
Base project Imp' cost (£k) | [13 empty] | 4366.1262 | 4280.8384 | 2490.5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11137.4785 | 0
Project Imp' risk (£k) | [13 empty] | 338.2964 | 348.4453 | 358.8986 | 3326.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4372.6306 | 0
Base sales forecast (£k) | [13 empty] | 0 | 0 | 0 | 9315.573 | 9595.0402 | 9882.8914 | 10179.3781 | 10484.7595 | 10799.3022 | 11123.2813 | 0 | 71380.2257 | 0
Sales rate risk (£k) | [13 empty] | 0 | 0 | 0 | 1863.1146 | 1919.008 | 1976.5783 | 2035.8756 | 2096.9519 | 2159.8604 | 2224.6563 | 0 | 14276.0451 | 0
Base cost of sales (£k) | [13 empty] | 0 | 0 | 0 | 2917.1051 | 3004.6183 | 3094.7568 | 3187.5995 | 3283.2275 | 3381.7244 | 3483.1761 | 0 | 22352.2078 | 0
Operations risk (£k) | [13 empty] | 0 | 0 | 0 | 3460.07 | 137.072 | 141.1842 | 145.4197 | 149.7823 | 154.2757 | 158.904 | 0 | 4346.7079 | 0
Tax reliefs and credits (£k) | [13 empty] | 470.4423 | 1464.9704 | 1270.9787 | 939.6239 | 708.6489 | 0 | 0 | 0 | 0 | 0 | 0 | 4854.6642 | 0
Tax on profits (£k) | [13 empty] | 0 | 0 | 0 | 107.5283 | 560.9625 | 920.4714 | 948.0855 | 976.5281 | 1005.8239 | 1035.9987 | 525.6545 | 6081.053 | 0
Cash flow (£k) | [13 empty] | -4233.9803 | -3164.3133 | -1578.4339 | -1419.6115 | 4682.0283 | 3749.9007 | 3862.3977 | 3978.2697 | 4097.6177 | 4220.5463 | -525.6545 | 13668.7669
Mid-year discount factor | [13 empty] | 0.94072 | 0.8325 | 0.73672 | 0.65197 | 0.57696 | 0.51059 | 0.45185 | 0.39986 | 0.35386 | 0.31315 | 0.27713
Cash flow Present Value (£K) | [13 empty] | -3982.9937 | -2634.2792 | -1162.8676 | -925.5395 | 2701.3511 | 1914.6453 | 1745.2077 | 1590.7645 | 1449.9889 | 1321.6713 | -145.6722 | 1872.2765 | 0
Cumulative NPV (£K) | [13 empty] | -3982.9937 | -6617.2729 | -7780.1405 | -8705.68 | -6004.3289 | -4089.6836 | -2344.476 | -753.7115 | 696.2774 | 2017.9487 | 1872.2765
Notes
1. For numerical cells, Black bold font represents the NPV model inputs. Non-bold font numerical cells are calculated.
2. Purple bold font represents the NPV Model output (at Cell AB114)
3. Check cells are designed to identify errors and will be filled light red in the event of an error being detected
4. The model's cost apportionment inputs are contained in the hidden colums D - O
5. This is a variant of model 4.1 which incorporates peer review changes including the modelling of inflation effects

## Sheet2
NPV Results calculation (£k) |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Total
a | Base project Imp' cost | 4366.1262 | 4280.8384 | 2490.5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11137.4785
b | Project implementation risk | 338.2964 | 348.4453 | 358.8986 | 3326.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4372.6306
c | Base sales forecast | 0 | 0 | 0 | 9315.573 | 9595.0402 | 9882.8914 | 10179.3781 | 10484.7595 | 10799.3022 | 11123.2813 | 0 | 71380.2257
d | Sales rate risk | 0 | 0 | 0 | 1863.1146 | 1919.008 | 1976.5783 | 2035.8756 | 2096.9519 | 2159.8604 | 2224.6563 | 0 | 14276.0451
e | Base cost of sales | 0 | 0 | 0 | 2917.1051 | 3004.6183 | 3094.7568 | 3187.5995 | 3283.2275 | 3381.7244 | 3483.1761 | 0 | 22352.2078
f | Operations risk | 0 | 0 | 0 | 3460.07 | 137.072 | 141.1842 | 145.4197 | 149.7823 | 154.2757 | 158.904 | 0 | 4346.7079
g | Tax reliefs and credits | 470.4423 | 1464.9704 | 1270.9787 | 939.6239 | 708.6489 | 0 | 0 | 0 | 0 | 0 | 0 | 4854.6642
h | Tax on profits | 0 | 0 | 0 | 107.5283 | 560.9625 | 920.4714 | 948.0855 | 976.5281 | 1005.8239 | 1035.9987 | 525.6545 | 6081.053
Net Cash flow = c+g-a-b-d-e-f-h |  | -4233.9803 | -3164.3133 | -1578.4339 | -1419.6115 | 4682.0283 | 3749.9007 | 3862.3977 | 3978.2697 | 4097.6177 | 4220.5463 | -525.6545 | 13668.7669
Mid-year discount factor |  | 0.94072 | 0.8325 | 0.73672 | 0.65197 | 0.57696 | 0.51059 | 0.45185 | 0.39986 | 0.35386 | 0.31315 | 0.27713
Cash flow Present Value |  | -3982.9937 | -2634.2792 | -1162.8676 | -925.5395 | 2701.3511 | 1914.6453 | 1745.2077 | 1590.7645 | 1449.9889 | 1321.6713 | -145.6722 | 1872.2765
Cumulative NPV |  | -3982.9937 | -6617.2729 | -7780.1405 | -8705.68 | -6004.3289 | -4089.6836 | -2344.476 | -753.7115 | 696.2774 | 2017.9487 | 1872.2765