## Model 5.1 - ModelRisk
Model 5.1 | Used by the book Net Present Value and Risk Modelling for Projects (Hopkinson, 2016) published by Routledge
Simulation uses ModelRisk - visit www.vosesoftware.com to download free trial license of the ModelRisk tool
Net Present Value Risk Model for the New Factory Project
Risk Model Inputs |  |  |  |  | Apportionment | [11 empty] | Costs and benefits simulated by year
| Cost (£k) |  |  |  | T = 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total | T = 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total | Check
| Min | Mode | Max | Simulated
Land for new factory |  | 2000 |  | 2000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0
In-house engineering team | 450 | 700 | 1000 | #NAME? | 0 | 0.4 | 0.4 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Design contract | 1600 | 2300 | 3000 | #NAME? | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Building contract | 20000 | 28000 | 40000 | #NAME? | 0 | 0.25 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Equipment contract | 34000 | 40000 | 46000 | #NAME? | 0 | 0 | 0.66667 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Factory handover | 1400 | 1600 | 2000 | #NAME? | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Project Management | 3000 | 3500 | 4200 | #NAME? | 0 | 0.33333 | 0.33333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Benefits (£k)
| Min | Mode | Max | Simulated
Sale of old site | 1500 | 2000 | 2500 | #NAME? | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Annual profit increase | 18000 |  | 22000 | #NAME? | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
NPV Results calculation | [16 empty] | T = 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Project cost (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Project benefits value (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
In-year Net value (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Discount Rate | 6%
Discount factor (using D = 6%) | [16 empty] | 1 | 0.97129 | 0.91631 | 0.86444 | 0.81551 | 0.76935 | 0.7258 | 0.68472 | 0.64596 | 0.6094 | 0.5749
In-year Net Present Value (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Cumulative NPV (£k) | [16 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Notes
1. The cost and benefits amortisation inputs are in the hidden colums F - R. Note that, given that these values are fixed, the effect of schedule risk is not included in the model.
2. Discount factors are calculated to correspond to mid-year values
3. Risk estimating inputs are colour coded Optimistic, Mode and Pessimistic
4. Brown font represents the Monte Carlo simulation input cells
5. Purple font represents the Monte Carlo simulation output (at Cell AE30)
6. The Check cells verify that model the is internally coherent. Check cells fill becomes red where this is not the case.
7. This example does not include any correlation of inputs. See Model 4.2. for the same model, but with correlation on selected cost inputs.