## Model 6.2 - ModelRisk
Model 6.2 | Used by the book Net Present Value and Risk Modelling for Projects (Hopkinson, 2016) published by Routledge
Simulation uses ModelRisk - visit www.vosesoftware.com to download free trial license of the ModelRisk tool
Net Present Value Risk Model for a Stores Modification Project (includes example of a ramp up of benefits and associated schedule risk)
Detailed Apportionment calculations - based on six mutually exclusive conditions (A-F)
Cost and Benefits |  |  |  |  | Schedule Risk |  | Apportionment (dates mark commencement points for each year) | [22 empty] | Condition A (Activity start and finish dates precede Year start and finish dates) | [19 empty] | Condition B (Activity start date precedes Year start and Activity finish date falls after Year start and up to and including Year finish date) | [19 empty] | Condition C (Activity start date precedes Year start and Activity finish falls after Year finish date) | [19 empty] | Condition D (Activity start date falls on after Year start and Activity finish falls before Year finish date) | [19 empty] | Condition E (Activity start date falls between Year start and finish dates and Activity finish falls after Year finish date) | [19 empty] | Condition F (Activity start and finish postdate Year start and finish dates)
| Cost (£k) | [5 empty] | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 | 2022-01-01 | 2023-01-01 | 2024-01-01 | 2025-01-01 | 2026-01-01 | [12 empty] | Condition A applicable Yes/No | [9 empty] | In-year apportionment in the case where Condition A is applicable | [9 empty] | Condition B applicable Yes/No | [9 empty] | In-year apportionment in the case where Condition B is applicable | [9 empty] | Condition C applicable Yes/No | [9 empty] | In-year apportionment in the case where Condition C is applicable | [9 empty] | Condition D applicable Yes/No | [9 empty] | In-year apportionment in the case where Condition D is applicable | [9 empty] | Condition E applicable Yes/No | [9 empty] | In-year apportionment in the case where Condition E is applicable | [9 empty] | Condition F applicable Yes/No | [9 empty] | In-year apportionment in the case where Condition F is applicable | [9 empty] | Checksum for Apportionment conditions (should aggregate to 1 for each year)
| Min | Mode | Max | Simulated | Start | Finish | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Check | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total | Check | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Project Design | 2400 | 2800 | 3400 | #NAME? | 2016-01-01 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Store modifications (200 Off) | 40000 | 55000 | 75000 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Proj' M'ment @ £1,500k/annum |  | 1500 |  | #NAME? | 2016-01-01 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Benefits (£k)
| Min | Mode | Max | Simulated
Annual profit increase per store | 20 | 80 | 200 | #NAME?
Annual profit increase for 200 stores |  |  |  | #NAME?
Profit increase during ramp-up period from Store 1 to Store 200 |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Profit increase from date of last store modification |  |  |  | #NAME? | #NAME? | 2025-12-31 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Schedule | Duration (months) |  |  | Simulated | Start | Finish
| Min | Mode | Max | (days)
Project lifecycle |  |  |  |  | 2016-01-01 | 2025-12-31
Design and Planning | 8 | 10 | 12 | #NAME? | 2016-01-01 | #NAME?
Store modifications | 20 | 24 | 36 | #NAME? | #NAME? | #NAME?
Full benefits realisation |  |  |  | #NAME? | #NAME? | 2025-12-31
NPV Results calculation | [17 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total | Check
Project cost (£k) | [17 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Project benefits value (£k) | [17 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
In-year Net value (£k) | [17 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Discount Rate | 6%
Discount factor (using D = 6%) | [17 empty] | 0.97129 | 0.91631 | 0.86444 | 0.81551 | 0.76935 | 0.7258 | 0.68472 | 0.64596 | 0.6094 | 0.5749
In-year Net Present Value (£k) | [17 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Cumulative NPV (£k) | [17 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Notes
1. This example simulated schedule risk in a similar way to Model 6.2, but includes one component (row 16) in which there is a ramp-up
2. The cost and benefits apportionment values are in the hidden colums J - U. The apportionment calculations are in columns AI - FU.
3. The ramp-up apportionment calculation is based on a steady rate of change (area under curve with constant gradient)and is filled in light blue.
4. Risk estimating inputs are colour coded Optimistic, Mode and Pessimistic
5. Brown font represents the Monte Carlo simulation input cells
6. Purple font represents the Monte Carlo simulation output (at Cell AF37)
7. The Check cells verify that the model is internally coherent. Check cells fill becomes red where this is not the case.
Formulas:
Start = [Start, row above]